{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["附件2"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"附件2","index":0,"n_rows":5,"n_cols":44,"rows_kept":5,"merged":[[0,0,0,43],[1,0,1,4],[2,0,3,0],[2,1,3,1],[2,2,3,2],[2,3,3,3],[2,4,3,4],[2,5,2,20],[2,21,3,21],[2,22,3,22],[2,23,2,43]],"flags":["formulas_cached_only"]}
["蓬江区新增专项债券资金用途调整明细表"]
["单位（盖章）：                         ",{"$nulls":42},"单位：万元"]
["序号","地市","债券全称","发行年度","债券类型（土储专项债券/棚改专项债券/其他专项债券）","原项目信息",{"$nulls":15},"调整情形（项目实施过程重大变化导致资金需求减少/项目竣工债券资金结余/按照监督检查和审计等意见调整/其他需要调整情形）","调整具体原因","拟调整项目信息"]
[{"$nulls":5},"区划编码","县区","项目名称","项目编码","项目类型（土储项目/棚改项目/交通基础设施项目/能源项目/农林水利项目/生态环保项目/社会事业项目/城乡冷链物流基础设施项目/市政与产业园区基础设施项目/保障性住房项目/其他有收益的公益性项目）","项目主管部门","项目建设单位","建设状态（未开工/在建/已竣工）","发行时安排债券金额","其中：用于项目资本金金额","以前年度是否发生债券资金用途调整（是/否）","本次拟调整用途金额","其中：用于项目资本金金额","调整后原项目剩余未使用债券金额","其中：用于项目资本金金额","调整后原项目剩余债券资金，预计使用完毕时间（年月）",null,null,"区划编码","县区","项目名称","项目编码","项目类型（土储项目/棚改项目/交通基础设施项目/能源项目/农林水利项目/生态环保项目/社会事业项目/城乡冷链物流基础设施项目/市政与产业园区基础设施项目/保障性住房项目/其他有收益的公益性项目）","拟调整项目与原项目是否属于同一类型（是/否）","如拟调整项目与原项目不属于同一类型，请解释说明","项目建设期限（预计至哪一年）","项目运营周期（预计至哪一年）","建设状态（未开工/在建/已竣工）","预计竣工日期","以前年度已安排债券资金金额","是否纳入国家发改委要求优先安排项目清单（是/否）","是否纳入财政部审核通过项目清单（是/否）","省政府同意上报时申报的专项债券金额","2021年已安排债券资金金额","本次拟安排债券金额","其中：用于项目资本金金额","是否属于补办调整手续（即市县已自行调整至该项目使用）（是/否）","预计使用完毕时间（年月）","备注"]
[1,"江门市","2021年广东省政府专项债券（七十五期）",2021,"其他专项债券",440703,"蓬江区","江门市蓬江区应急救治与医疗卫生补短板建设项目",860,"社会事业项目","江门市蓬江区卫生健康局","江门市蓬江区卫生健康局","在建",2000,0,"否",1000,0,1000,0,"2021-12-31","其他需要调整情形","由于该项目前期工作开展时间长，涉及邻避等问题，结合项目实际情况，预计1000万元债券资金无法在12月底前实际使用完毕。",440703,"蓬江区","江门市蓬江区城乡污水治理项目",887,"生态环保项目","否","经全面梳理，我区社会事业类项目资金需求已基本满足。但江门市蓬江区城乡污水治理项目年度内仍有资金需求。","2023年","2030年","在建","2023-06-30",80000,"否","是",50000,45000,1000,0,"否","2021-12-31"]