{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["汇总表"],"not_rendered":{"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"汇总表","index":0,"n_rows":17,"n_cols":11,"rows_kept":17,"merged":[[1,0,1,10],[16,0,16,2]]}
["附件"]
["江门市蓬江区2025年度（第三批）自然人户用分布式光伏项目明细表"]
["编号","项目名称","项目建设地点","项目建设规模 (kW)","项目投资人","实施计划（动工-竣工时间）","建设方式","光伏电力用户","光伏电力消纳方式","并网电压等级(V)","自发自用比例(%)"]
[1,"钟朝霞个人住宅光伏发电项目","广东省江门市蓬江区五邑碧桂园阳光六街33号",12,"钟朝霞","2025年4月30日-2025年5月28日","屋顶","钟朝霞","自发自用为主，余量上网",380,30]
[2,"蓝柏进个人住宅光伏发电项目","广东省江门市蓬江区环市街道办事处联合社区居委会潮江里4-2（全额上网）",20,"蓝柏进","2025年5月21日-2025年5月26日","屋顶","蓝柏进","全额上网",380,0]
[3,"饶玉飚个人住宅光伏发电项目","广东省江门市蓬江区杜阮镇灏景园凯旋一街11号",17,"饶玉飚","2025年4月20日-2025年5月28日","屋顶","饶玉飚（康嘉裕共同拥有，收益说明）","自发自用为主，余量上网",380,30]
[4,"李礼剑个人住宅光伏发电项目","广东省江门市蓬江区杜阮镇帕佳图天玥花园81号",10,"李礼剑","2022年12月20日-2025年5月28日","屋顶","李礼剑（李淑英共同拥有，收益说明）","自发自用为主，余量上网",380,30]
[5,"徐海燕个人住宅光伏发电项目","广东省江门市蓬江区杜阮镇子棉美塘16号",25,"徐海燕","2025年5月21日-2025年5月28日","屋顶","李燕泽（翁媳关系，收益说明）","自发自用为主，余量上网",380,30]
[6,"金云琦个人住宅光伏发电项目","广东省江门市蓬江区杜阮镇灏景园棕榈街17号",20,"金云琦","2025年5月28日-2025年5月30日","屋顶","金云琦（李芝田共同拥有，收益说明）","自发自用为主，余量上网",380,30]
[7,"尹永沛个人住宅光伏发电项目","广东省江门市蓬江区杜阮镇木朗村五和里126号",25,"尹永沛","2024年9月10日-2025年5月30日","屋顶","尹永沛","自发自用为主，余量上网",380,30]
[8,"胡建仁个人住宅光伏发电项目","广东省江门市蓬江区荷塘镇塔岗村中大街17号",40,"胡建仁","2025年2月27日-2025年5月23日","屋顶","胡建仁","自发自用剩余电量上网",380,30]
[9,"冯丽个人住宅光伏发电项目","广东省江门市蓬江区荷塘镇南村上村仙井里五巷3号",25,"冯丽","2025年5月7日-2025年5月21日","屋顶","胡健钊（收益说明）","自发自用剩余电量上网",380,30]
[10,"伍兆勤个人住宅光伏发电项目","广东省江门市蓬江区荷塘镇唐溪村土牛大街六巷6号",25,"伍兆勤","2025年4月25日-2025年5月23日","屋顶","伍兆勤","自发自用剩余电量上网",380,30]
[11,"陈资成个人住宅光伏发电项目","广东省江门市蓬江区芝山恩荣里31号",17,"陈资成","2025年5月26日-2025年5月28日","屋顶","陈国盈（父子关系，收益说明）","自发自用剩余电量上网",380,30]
[12,"覃水秀个人住宅光伏发电项目","广东省江门市蓬江区荷塘镇为民村闲步新村大路东三巷15号",30,"覃水秀","2025年5月27日-2025年5月29日","屋顶","覃水秀","自发自用剩余电量上网",380,30]
[13,"陈伟恒个人住宅光伏发电项目","广东省江门市蓬江区荷塘镇为民村闲步新村大路东四巷14号",40,"陈伟恒","2025年5月27日-2025年5月29日","屋顶","陈伟恒","自发自用剩余电量上网",380,30]
["合计：",null,null,{"$f":"SUM(D4:D16)","v":306}]